## 1.Feeder Deployment Incremental
TABLE 1 | Feeder Deployment Incremental |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
This table presents the required format for the reporting of the incremental deployment of grid modernization technologies at the feeder/substation level during the plan year.
Feeder/Substation Identification | [7 empty] | Monitoring & Control (SCADA) | [5 empty] | Distribution Automation |  |  |  | Volt-Var Optimization |  |  |  |  | Advanced Distribution Management System (ADMS) |  |  | Communications |  | Workforce Management
Company Name | Division Name | District Name | Substation Name | Substation Location (City/Town) | Feeder ID | Feeder Location (Cities/Towns) (1) | Initial Inclusion of Feeder in Report (Y/N) (2) | Microprocessor Relay | 4kV Circuit Breaker SCADA | Recloser SCADA | Padmount Switch SCADA | Network Protector SCADA | OMS/AMI Integration | OH DA | OH DA w/Ties | 4kV Oil Switch Replacement | 4kV VFI Retrofit for DA | VVO - Regulators | VVO - Capacitor Banks | VVO - LTC Controls | VVO - Line Sensors | VVO - IT Work | Advanced Load Flow | GIS Survey (Expense) | Dist. Management System | Numbers of Nodes | Miles of Fiber | Mobile Damage Assessment
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W1 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W2 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W4 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W6 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H10 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H11 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11W11 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W14 | Townsend | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W15 | Townsend | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W16 | Townsend, Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W17 | Townsend | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H22 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H24 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg | 1341 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W1 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W2 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W3 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W8 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W10 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W11 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W12 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W17 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | Network | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W27 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W28 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W29 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W30 | Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W31 | Lunenburg, Townsend, Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W34 | Lunenburg, Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W37 | Lunenburg, Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W38 | Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg | 35W36 | Fitchburg, Ashby | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W18 | Townsend, Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W19 | Townsend, Ashby | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W38 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W39 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W40 | Fitchburg, Ashby, Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W42 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1303 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1309 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W51 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W53 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W54 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W55 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W56 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NOTES
Data in entry cells of template is for reference only and should be overwritten with actual Company provided data. Please add rows for each additional substation/feeder as necessary.
(1) For each feeder reported, identify all cities and towns (separated by commas) where customers served by the feeder are located.
(2) Enter "Y" for a feeder that is included in an Annual Report for the first time or "N" for a feeder that was included in a previous Annual Report.
(3) For each substation reported, include a row that identifies all grid modernization technologies deployed at the substation level.
(4) For each cell I7 through AC7, please populate cells with: (i) a number, (ii) Yes/No, or (iii) other (provide explanation).

## 2. Feeder Deployment Cumulative
TABLE 2 | Feeder Deployment Cumulative |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
This table presents the required format for the reporting of the cumulative deployment of grid modernization technologies at the feeder/substation level at the end of the plan year.
Feeder/Substation Identification | [7 empty] | Monitoring & Control (SCADA) | [5 empty] | Distribution Automation |  |  |  | Volt-Var Optimization |  |  |  |  | Advanced Distribution Management System (ADMS) |  |  | Communications |  | Workforce Management
Company Name | Division Name | District Name | Substation Name | Substation Location (City/Town) | Feeder ID | Feeder Location (Cities/Towns) (1) | Initial Inclusion of Feeder in Report (Y/N) (2) | Microprocessor Relay | 4kV Circuit Breaker SCADA | Recloser SCADA | Padmount Switch SCADA | Network Protector SCADA | OMS/AMI Integration | OH DA | OH DA w/Ties | 4kV Oil Switch Replacement | 4kV VFI Retrofit for DA | VVO - Regulators | VVO - Capacitor Banks | VVO - LTC Controls | VVO - Line Sensors | VVO - IT Work | Advanced Load Flow | GIS Survey (Expense) | Dist. Management System | Numbers of Nodes | Miles of Fiber | Mobile Damage Assessment
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W1 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W2 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W4 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W6 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H10 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H11 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11W11 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W14 | Townsend | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W15 | Townsend | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W16 | Townsend, Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W17 | Townsend | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H22 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H24 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg | 1341 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W1 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W2 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W3 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W8 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W10 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W11 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W12 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W17 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | Network | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W27 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W28 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W29 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W30 | Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W31 | Lunenburg, Townsend, Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W34 | Lunenburg, Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W37 | Lunenburg, Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W38 | Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg | 35W36 | Fitchburg, Ashby | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W18 | Townsend, Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W19 | Townsend, Ashby | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W38 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W39 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W40 | Fitchburg, Ashby, Lunenburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W42 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1303 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1309 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W51 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W53 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W54 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W55 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W56 | Fitchburg | Y | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg |  |  |  | 0 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NOTES
Data in entry cells of template is for reference only and should be overwritten with actual Company provided data. Please add rows for each additional substation/feeder as necessary.
(1) For each feeder reported, identify all cities and towns (separated by commas) where customers served by the feeder are located.
(2) Enter "Y" for a feeder that is included in an Annual Report for the first time or "N" for a feeder that was included in a previous Annual Report.
(3) For each substation reported, include a row that identifies all grid modernization technologies deployed at the substation level.
(4) For each cell I7 through AC7, please populate cells with: (i) a number, (ii) Yes/No, or (iii) other (provide explanation).

## 3. Feeder Status
TABLE 3 | Feeder Status |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
This table presents the required format for the reporting of the following information at the feeder/substation level:
(1) Feeder Characteristics
(2) Feeder Grid Modernization Capability at End of Plan Year
(3) DER Interconnections
(4) EV Charging Infrastructure( Eversource only) | [12 empty] | 451348.669
(5) Performance Metrics
Feeder/Substation Identification & Location | [7 empty] | Feeder Characteristics | [7 empty] | Feeder Grid Modernization Capability at End of Plan Year |  | DER Interconnections (7) | [24 empty] | Eversource EV Charging Infrastructure | [7 empty] | State-Wide Performance Metrics | [26 empty] | Company-Specific Performance Metrics
[18 empty] | # of DER Facilities | [7 empty] | Nominal DER Capacity (in kW) | [8 empty] | Estimated Annual DER Energy Output (in kWh) | [15 empty] | VVO-Related | [11 empty] | DMS-Power Flow and Control Capabilities |  | Control Functions |  |  | Customers Benefitting from GMP Investments |  | Reliability-Related - Outage Duration and Frequency | [7 empty] | Eversource |  |  | National Grid |  | Unitil
[18 empty] | DER Type 1 [SOLAR] |  | DER Type 2 [GAS] |  | DER Type 3 [N/A] |  | Total (All DER Types) |  | DER Type 1 [SOLAR] |  | DER Type 2 [GAS] |  | DER Type 3 [N/A] |  | Total (All DER Types) |  | % DER Capacity to Peak Demand | DER Type 1 [SOLAR] |  | DER Type 2 [GAS] |  | DER Type 3 [N/A] |  | Total (All DER Types) | [28 empty] | Outage Duration and Frequency | [7 empty] | Advanced Load Flow Milestone | Average Protective Zone Size |  | Main Line Customer Minutes of Interruption
Company Name | Division Name | District Name | Substation Name | Substation Location (City/Town) | Feeder ID | Feeder Location (Cities/Towns) (1) | Initial Inclusion of Feeder in Report (Y/N) (2) | Feeder Type (Overhead/ Underground) | System Voltage (in kV) | Feeder Capacity Rating (in MVA) | Feeder Length (in miles) | Current Customers Count | Annual Energy Delivered (in kWh) | Annual Energy Delivered (Metered/ Estimated) (4) | Annual Peak Load (MVA) | Automation Capability (Full/Partial/No) (5) | VVO Capability (Full/Partial/No) (6) | Total # of Facilities Interconnected on Feeder | # of Customer-Owned Facilities Interconnected on Feeder | Total # of Facilities Interconnected on Feeder | # of Customer-Owned Facilities Interconnected on Feeder | Total # of Facilities Interconnected on Feeder | # of Customer-Owned Facilities Interconnected on Feeder | Total # of DER Facilities Interconnected on Feeder | # of Customer-Owned DER Facilities Interconnected on Feeder | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (in kW) | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (in kW) | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (in kW) | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (kW) | Total Nominal Capacity (all DER types)/Feeder Peak Demand | Estimated Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | # of Charging Sites Activated | # of Charging Ports Activated | Locations of Charging Sites (Towns/Cities) | # of Level 2 Charging Ports | Total Capacity of Level 2 Charging Ports (kW) | # of DCFC Charging Ports | Total Capacity of DCFC Charging Ports (kw) | Types of Charging Sites (e.g. public site, work place, MUD, EJ community) | Estimated Annual Energy Delivered w/o VVO (kWh) | Annual Energy Saving w/ VVO (kWh) | Estimated Annual Peak Load w/o VVO (MVA) | Annual Peak Load Reduction w/ VVO (MVA) | Estimated Distribution Losses w/o VVO (kWh) | Reduction of Distribution Losses w/VVO (kWh) | Estimated Power Factor w/o VVO | Power Factor w/ VVO | Estimated GHG Emissions w/o VVO (metric tons) | Reduction of GHG Emissions w/ VVO (metric tons) | # of Voltage Complaints, Plan Year (Unitil Note 1) | Change in # of Voltage Complaints (Baseline minus Plan Year) (8) | DMS Power Flow Capabilities (Y/N) (9) | # of Customers Benefiting from DMS Power Flow Capability | Control Function Implemented (Y/N) (10) | Type of Control Function(s) Implemented | # of Customers Benefitting from Control Function | # of Customers Benefiting from DA Devices | Types of DA Devices Benefiting Customers | Feeder Level SAIDI w/Excludable Major Events, Plan Year | Change in Feeder Level SAIDI w/Excludable Major Events (Baseline minus Plan Year) (11) | Feeder Level SAIDI w/o Excludable Major Events, Plan Year | Change in Feeder Level SAIDI w/o Excludable Major Events (Baseline minus Plan Year) (11) | Feeder Level SAIFI w/Excludable Major Events, Plan Year | Change in Feeder Level SAIFI w/Excludable Major Events (Baseline minus Plan Year) (11) | Feeder Level SAIFI, Plan Year, w/o Excludable Major Events | Change in Feeder Level SAIFI w/o Excludable Major Events (Baseline minus Plan Year) (11) | Advanced Load Flow (Static, Semi-Auto 1, Semi-Auto 2, Full) (12) | Average Protective Zone Size, Plan Year (in # customers) (13) | Change in Average Protective Zone Size (Baseline minus Plan Year) (14) | Customer Minutes of Interruption, Plan Year (15) | Change in Customer Minutes of Interruption (Baseline minus Plan Year) (16) | Customer Minutes Saved, Plan Year (17)
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W1 | Fitchburg | Y | Overhead | 13.8 kV | 6.2156 | 5.8371 | 391 | 17204487.2859 | Estimated | 4 | No | No | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 446.16 | 446.16 | 0 | 0 | 0 | 0 | 446.16 | 446.16 | 11.15% | 726955.2576 | 726955.2576 | 0 | 0 | 0 | 0 | 726955.2576 | 726955.2576 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17204487.2859 | 0 | 4 | 0 | 762.6958 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0.33333 |  | 0 | N | N/A | 0 | N/A | N/A | 66.11 | -91.0733 | 66.11 | 21.0533 | 1.005 | -0.73633 | 1.005 | 0.69567 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W2 | Fitchburg | Y | Overhead | 13.8 kV | 8.9156 | 9.3707 | 1940 | 12903365.4644 | Estimated | 3 | No | No | 57 | 57 | 1 | 1 | 0 | 0 | 58 | 58 | 612.65 | 612.65 | 1.2 | 1.2 | 0 | 0 | 613.85 | 613.85 | 20.46% | 998227.404 | 998227.404 | 10512 | 10512 | 0 | 0 | 1008739.404 | 1008739.404 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12903365.4644 | 0 | 3 | 0 | 572.0219 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1 |  | 0 | N | N/A | 0 | N/A | N/A | 15.91 | -151.6033 | 9.07 | -33.57 | 0.431 | -1.988 | 0.155 | -0.931 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W4 | Fitchburg | Y | Overhead | 13.8 kV | 9.5609 | 8.9631 | 1639 | 10107636.2805 | Estimated | 2.35 | No | No | 43 | 43 | 0 | 0 | 0 | 0 | 43 | 43 | 785.89 | 785.89 | 0 | 0 | 0 | 0 | 785.89 | 785.89 | 33.44% | 1280497.7304 | 1280497.7304 | 0 | 0 | 0 | 0 | 1280497.7304 | 1280497.7304 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10107636.2805 | 0 | 2.35 | 0 | 448.0838 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.3333 |  | 0 | N | N/A | 0 | N/A | N/A | 279.45 | 116.5333 | 273.49 | 211.4667 | 3.175 | 0.68967 | 3.101 | 1.7377 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W6 | Fitchburg | Y | Overhead | 13.8 kV | 8.9156 | 0.82804 | 1 | 2860246.0113 | Estimated | 0.665 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2860246.0113 | 0 | 0.665 | 0 | 126.7982 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H10 | Fitchburg | Y | Overhead | 4.16 kV | 2.0175 | 3.866 | 736 | 4483365.8155 | Estimated | 1.0424 | No | No | 27 | 27 | 0 | 0 | 0 | 0 | 27 | 27 | 203.02 | 203.02 | 0 | 0 | 0 | 0 | 203.02 | 203.02 | 19.48% | 330792.6672 | 330792.6672 | 0 | 0 | 0 | 0 | 330792.6672 | 330792.6672 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4483365.8155 | 0 | 1.0424 | 0 | 198.753 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 28.12 | -105.2167 | 0 | -51.5933 | 1.001 | -1.289 | 0 | -1.1437 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H11 | Fitchburg | Y | Overhead | 4.16 kV | 2.0175 | 2.6698 | 372 | 4318080.4398 | Estimated | 1.0039 | No | No | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 37.13 | 37.13 | 0 | 0 | 0 | 0 | 37.13 | 37.13 | 3.698% | 60498.1368 | 60498.1368 | 0 | 0 | 0 | 0 | 60498.1368 | 60498.1368 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4318080.4398 | 0 | 1.0039 | 0 | 191.4257 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 43.52 | -89.08 | 16.47 | -45.41 | 1.212 | -0.88733 | 0.212 | -0.89067 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11W11 | Fitchburg | Y | Overhead | 13.8 kV | 12.6921 | 19.6011 | 1718 | 16997375.8939 | Estimated | 3.9518 | No | No | 90 | 90 | 0 | 0 | 0 | 0 | 90 | 90 | 788.93 | 788.93 | 0 | 0 | 0 | 0 | 788.93 | 788.93 | 19.96% | 1285450.9848 | 1285450.9848 | 0 | 0 | 0 | 0 | 1285450.9848 | 1285450.9848 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 16997375.8939 | 0 | 3.9518 | 0 | 753.5143 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.3333 |  | 0 | N | N/A | 0 | N/A | N/A | 60.6 | -30.1367 | 31.09 | -35.7467 | 1.59 | 0.064333 | 0.57 | -0.25833 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W14 | Townsend | Y | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W15 | Townsend | Y | Overhead | 13.8 kV | 9.5609 | 0.075962 | 1 | 15797964.2885 | Estimated | 3.673 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15797964.2885 | 0 | 3.673 | 0 | 700.3429 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 61 | -29.91 | 0 | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W16 | Townsend, Lunenburg | Y | Overhead | 13.8 kV | 7.6487 | 41.116 | 1500 | 23439929.6602 | Estimated | 5.4497 | No | No | 139 | 139 | 0 | 0 | 0 | 0 | 139 | 139 | 1619.79 | 1619.79 | 0 | 0 | 0 | 0 | 1619.79 | 1619.79 | 29.72% | 2639221.0344 | 2639221.0344 | 0 | 0 | 0 | 0 | 2639221.0344 | 2639221.0344 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 23439929.6602 | 0 | 5.4497 | 0 | 1039.1205 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1 |  | 0 | N | N/A | 0 | N/A | N/A | 116.28 | -130.5533 | 54.73 | -32.4067 | 1.593 | -1.1347 | 0.585 | -0.73233 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W17 | Townsend | Y | Overhead | 13.8 kV | 9.5609 | 11.4409 | 557 | 6202671.4452 | Estimated | 1.4421 | No | No | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 365.695 | 365.695 | 0 | 0 | 0 | 0 | 365.695 | 365.695 | 25.36% | 595848.8052 | 595848.8052 | 0 | 0 | 0 | 0 | 595848.8052 | 595848.8052 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6202671.4452 | 0 | 1.4421 | 0 | 274.972 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0.33333 |  | 0 | N | N/A | 0 | N/A | N/A | 104.82 | -128.3667 | 43.36 | -8.9267 | 2.133 | 0.045333 | 1.127 | 0.432 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Townsend | Townsend | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H22 | Fitchburg | Y | Overhead | 4.16 kV | 2.1616 | 15.6295 | 898 | 7055619.4746 | Estimated | 1.6404 | No | No | 69 | 69 | 0 | 0 | 0 | 0 | 69 | 69 | 501.04 | 501.04 | 0 | 0 | 0 | 0 | 501.04 | 501.04 | 30.54% | 816374.5344 | 816374.5344 | 0 | 0 | 0 | 0 | 816374.5344 | 816374.5344 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7055619.4746 | 0 | 1.6404 | 0 | 312.7842 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 194.5 | 29.52 | 188.28 | 84.8767 | 3.165 | -0.011667 | 2.938 | 0.16833 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H24 | Fitchburg | Y | Overhead | 4.16 kV | 2.1616 | 2.0171 | 227 | 1570211.069 | Estimated | 0.36507 | No | No | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 12.27 | 12.27 | 0 | 0 | 0 | 0 | 12.27 | 12.27 | 3.361% | 19992.2472 | 19992.2472 | 0 | 0 | 0 | 0 | 19992.2472 | 19992.2472 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1570211.069 | 0 | 0.36507 | 0 | 69.6094 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 82.82 | -62.76 | 82.82 | -2.1 | 1.991 | -0.95567 | 1.991 | -0.61667 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg | 1341 | Fitchburg | Y | Overhead | 13.8 kV | 5.9039 | 2.7 | 1 | 205582.5239 | Estimated | 2.983 | No | No | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 205582.5239 | 0 | 2.983 | 0 | 568.7804 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W1 | Fitchburg | Y | Underground | 13.8 kV | 9.3219 | 11.7727 | 2060 | 19785160.3788 | Estimated | 4.6 | No | No | 26 | 26 | 2 | 2 | 0 | 0 | 28 | 28 | 348.36 | 348.36 | 61.2 | 61.2 | 0 | 0 | 409.56 | 409.56 | 8.903% | 567603.8496 | 567603.8496 | 536112 | 536112 | 0 | 0 | 1103715.8496 | 1103715.8496 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 19785160.3788 | 0 | 4.6 | 0 | 877.1002 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.6667 |  | 0 | N | N/A | 0 | N/A | N/A | 184.58 | 54.7233 | 182.98 | 127.2633 | 2.498 | 0.89367 | 2.48 | 1.5587 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W2 | Fitchburg | Y | Underground | 13.8 kV | 3.5853 | 1.1876 | Network | 0 | N/A | 0.669 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0.669 | 0 | 127.5609 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W3 | Fitchburg | Y | Underground | 13.8 kV | 3.7049 | 0.80366 | 19 | 3563965.9132 | Estimated | 0.82861 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3563965.9132 | 0 | 0.82861 | 0 | 157.9949 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 0 | -17.8 | 0 | -17.8 | 0 | -0.33333 | 0 | -0.33333 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W8 | Fitchburg | Y | Underground | 13.8 kV | 8.5331 | 1.4224 | Network | 0 | N/A | 0.637 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0.637 | 0 | 121.4593 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W10 | Fitchburg | Y | Underground | 13.8 kV | 8.5331 | 1.7918 | N/A | 0 | N/A | 1.944 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1.944 | 0 | 370.6702 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W11 | Fitchburg | Y | Underground | 13.8 kV | 8.5331 | 1.2636 | Network | 0 | N/A | 1.2 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1.2 | 0 | 228.8087 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W12 | Fitchburg | Y | Underground | 13.8 kV | 2.295 | 0.25012 | 0 | 0 | N/A | 0 | No | No | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 348.36 | 0 | 0 | 0 | 0 | 0 | 348.36 | 0 |  | 567603.8496 | 0 | 0 | 0 | 0 | 0 | 567603.8496 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W17 | Fitchburg | Y | Underground | 13.8 kV | 8.5331 | 1.717 | 1 | 4731234.0036 | Estimated | 1.1 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4731234.0036 | 0 | 1.1 | 0 | 209.7413 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 0 | -33.4167 | 0 | -32.86 | 0 | -1.111 | 0 | -0.83333 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | Network | Fitchburg | Y | Underground | 208 V | 9.8 | N/A | 487 | 10778611.2846 | Estimated | 2.506 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10778611.2846 | 0 | 2.506 | 0 | 477.8289 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0.33333 |  | 0 | N | N/A | 0 | N/A | N/A | 0.36468 | -74.681 | 0.36468 | -16.772 | 0.0020534 | -0.66269 | 0.0020534 | -0.32328 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W27 | Fitchburg | Y | Overhead | 13.8 kV | 9.5609 | 12.9608 | 1213 | 10726166.6428 | Estimated | 2.4938 | No | No | 86 | 86 | 0 | 0 | 0 | 0 | 86 | 86 | 892.49 | 892.49 | 0 | 0 | 0 | 0 | 892.49 | 892.49 | 35.79% | 1454187.5064 | 1454187.5064 | 0 | 0 | 0 | 0 | 1454187.5064 | 1454187.5064 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10726166.6428 | 0 | 2.4938 | 0 | 475.504 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.3333 |  | 0 | N | N/A | 0 | N/A | N/A | 73.53 | 58.7467 | 72.75 | 58.79 | 0.673 | 0.35167 | 0.552 | 0.239 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W28 | Fitchburg | Y | Overhead | 13.8 kV | 9.5609 | 9.2967 | 682 | 6021570.5501 | Estimated | 1.4 | No | No | 23 | 23 | 0 | 0 | 0 | 0 | 23 | 23 | 155.68 | 155.68 | 0 | 0 | 0 | 0 | 155.68 | 155.68 | 11.12% | 253658.7648 | 253658.7648 | 0 | 0 | 0 | 0 | 253658.7648 | 253658.7648 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6021570.5501 | 0 | 1.4 | 0 | 266.9435 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1 |  | 0 | N | N/A | 0 | N/A | N/A | 43.22 | -201.8667 | 43.22 | 23.8767 | 0.601 | 0.13933 | 0.601 | 0.35367 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W29 | Fitchburg | Y | Overhead | 13.8 kV | N/A | 0.0026261 | N/A | 0 | N/A | 0 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W30 | Lunenburg | Y | Overhead | 13.8 kV | 9.9434 | 45.8162 | 1328 | 20150114.9711 | Estimated | 4.6849 | No | No | 132 | 132 | 0 | 0 | 0 | 0 | 132 | 132 | 1474.21 | 1474.21 | 0 | 0 | 0 | 0 | 1474.21 | 1474.21 | 31.47% | 2402018.8056 | 2402018.8056 | 0 | 0 | 0 | 0 | 2402018.8056 | 2402018.8056 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20150114.9711 | 0 | 4.6849 | 0 | 893.2791 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.6667 |  | 0 | N | N/A | 0 | N/A | N/A | 456.69 | 172.1067 | 407.38 | 271.9667 | 5.081 | 2.218 | 4.008 | 2.122 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W31 | Lunenburg, Townsend, Fitchburg | Y | Overhead | 13.8 kV | 11.0142 | 45.4194 | 1637 | 17134451.506 | Estimated | 3.9837 | No | No | 97 | 97 | 0 | 0 | 0 | 0 | 97 | 97 | 4748.15 | 4748.15 | 0 | 0 | 0 | 0 | 4748.15 | 4748.15 | 119.2% | 7736445.684 | 7736445.684 | 0 | 0 | 0 | 0 | 7736445.684 | 7736445.684 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17134451.506 | 0 | 3.9837 | 0 | 759.591 | 0 | 0.95 | 0 | N/A | 0 | 0 | 2 |  | 0 | N | N/A | 0 | N/A | N/A | 398.97 | 205.8767 | 342.04 | 245.9533 | 4.288 | 2.0973 | 3.082 | 1.5127 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W34 | Lunenburg, Fitchburg | Y | Overhead | 13.8 kV | 12.6204 | 6.1512 | 1240 | 9218334.9102 | Estimated | 2.1432 | No | No | 29 | 29 | 0 | 0 | 0 | 0 | 29 | 29 | 151.84 | 151.84 | 0 | 0 | 0 | 0 | 151.84 | 151.84 | 7.085% | 247402.0224 | 247402.0224 | 0 | 0 | 0 | 0 | 247402.0224 | 247402.0224 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9218334.9102 | 0 | 2.1432 | 0 | 408.66 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.6667 |  | 0 | N | N/A | 0 | N/A | N/A | 77.56 | 7.7767 | 75.57 | 71.6833 | 1.347 | 0.27867 | 1.062 | 0.99367 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W37 | Lunenburg, Fitchburg | Y | Overhead | 13.8 kV | 11.4731 | 22.6044 | 1221 | 16654686.8638 | Estimated | 3.8722 | No | No | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 118 | 1469.55 | 1469.55 | 0 | 0 | 0 | 0 | 1469.55 | 1469.55 | 37.95% | 2394425.988 | 2394425.988 | 0 | 0 | 0 | 0 | 2394425.988 | 2394425.988 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 16654686.8638 | 0 | 3.8722 | 0 | 738.3225 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.6667 |  | 0 | N | N/A | 0 | N/A | N/A | 67.92 | -169.5933 | 67.19 | -14.9033 | 0.902 | -2.0053 | 0.889 | -0.62567 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W38 | Lunenburg | Y | Overhead | 13.8 kV | 12.6921 | 18.7711 | 1279 | 12645225.2114 | Estimated | 2.94 | No | No | 79 | 79 | 0 | 0 | 0 | 0 | 79 | 79 | 1775.71 | 1775.71 | 0 | 0 | 0 | 0 | 1775.71 | 1775.71 | 60.4% | 2893270.8456 | 2893270.8456 | 0 | 0 | 0 | 0 | 2893270.8456 | 2893270.8456 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12645225.2114 | 0 | 2.94 | 0 | 560.5782 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.3333 |  | 0 | N | N/A | 0 | N/A | N/A | 110.88 | -104.3 | 108.49 | 68.21 | 1.335 | -0.73667 | 1.308 | 0.65133 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg | 35W36 | Fitchburg, Ashby | Y | Overhead | 13.8 kV | 7.6487 | 23.2707 | 761 | 12624663.8696 | Estimated | 2.9352 | No | No | 89 | 89 | 0 | 0 | 0 | 0 | 89 | 89 | 3055.36 | 3055.36 | 0 | 0 | 0 | 0 | 3055.36 | 3055.36 | 104.1% | 4978281.3696 | 4978281.3696 | 0 | 0 | 0 | 0 | 4978281.3696 | 4978281.3696 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12624663.8696 | 0 | 2.9352 | 0 | 559.6667 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.6667 |  | 0 | N | N/A | 0 | N/A | N/A | 164.82 | -24.9033 | 148.05 | 106.6833 | 2.091 | 0.553 | 1.808 | 1.1503 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W18 | Townsend, Lunenburg | Y | Overhead | 13.8 kV | 12.6921 | 51.2203 | 1965 | 21726484.5096 | Estimated | 5.0514 | No | No | 118 | 118 | 0 | 0 | 0 | 0 | 118 | 118 | 923.49 | 923.49 | 0 | 0 | 0 | 0 | 923.49 | 923.49 | 18.28% | 1504697.6664 | 1504697.6664 | 0 | 0 | 0 | 0 | 1504697.6664 | 1504697.6664 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 21726484.5096 | 0 | 5.0514 | 0 | 963.1614 | 0 | 0.95 | 0 | N/A | 0 | 0 | 3 |  | 0 | N | N/A | 0 | N/A | N/A | 171.63 | -57.6067 | 163.76 | 94.8267 | 2.742 | 0.50133 | 1.735 | 0.87367 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W19 | Townsend, Ashby | Y | Overhead | 13.8 kV | 8.2606 | 61.9023 | 1299 | 12336805.0843 | Estimated | 2.8683 | No | No | 158 | 158 | 0 | 0 | 0 | 0 | 158 | 158 | 3969.34 | 3969.34 | 0 | 0 | 0 | 0 | 3969.34 | 3969.34 | 138.4% | 6467483.8224 | 6467483.8224 | 0 | 0 | 0 | 0 | 6467483.8224 | 6467483.8224 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12336805.0843 | 0 | 2.8683 | 0 | 546.9055 | 0 | 0.95 | 0 | N/A | 0 | 0 | 3.3333 |  | 0 | N | N/A | 0 | N/A | N/A | 156.56 | -258.0467 | 101.3 | 1.93 | 2.796 | -0.126 | 1.163 | -0.17367 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W38 | Fitchburg | Y | Overhead | 13.8 kV | 7.6726 | 0.60675 | 4 | 9462468.0073 | Estimated | 2.2 | No | No | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1800 | 1800 | 0 | 0 | 1800 | 1800 | 81.82% | 0 | 0 | 15768000 | 15768000 | 0 | 0 | 15768000 | 15768000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9462468.0073 | 0 | 2.2 | 0 | 419.4827 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 0 | -115.5833 | 0 | -66.25 | 0 | -1.0833 | 0 | -0.75 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W39 | Fitchburg | Y | Overhead | 13.8 kV | 9.5609 | 7.9157 | 420 | 13763589.8287 | Estimated | 3.2 | No | No | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 1252.98 | 1252.98 | 0 | 0 | 0 | 0 | 1252.98 | 1252.98 | 39.16% | 2041555.4928 | 2041555.4928 | 0 | 0 | 0 | 0 | 2041555.4928 | 2041555.4928 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 13763589.8287 | 0 | 3.2 | 0 | 610.1566 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0.66667 |  | 0 | N | N/A | 0 | N/A | N/A | 5.11 | -144.6333 | 5.11 | -94.0633 | 0.062 | -1.8083 | 0.062 | -1.471 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W40 | Fitchburg, Ashby, Lunenburg | Y | Overhead | 13.8 kV | 12.6921 | 18.537 | 1571 | 32688525.8432 | Estimated | 7.6 | No | No | 74 | 74 | 0 | 0 | 0 | 0 | 74 | 74 | 1677.24 | 1677.24 | 0 | 0 | 0 | 0 | 1677.24 | 1677.24 | 22.07% | 2732827.7664 | 2732827.7664 | 0 | 0 | 0 | 0 | 2732827.7664 | 2732827.7664 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 32688525.8432 | 0 | 7.6 | 0 | 1449.122 | 0 | 0.95 | 0 | N/A | 0 | 0 | 3 |  | 0 | N | N/A | 0 | N/A | N/A | 61.56 | -49.5967 | 61.56 | 1.79 | 1.136 | -0.13 | 1.136 | 0.23033 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W42 | Fitchburg | Y | Overhead | 13.8 kV | 9.5609 | 12.4351 | 1704 | 15053926.3752 | Estimated | 3.5 | No | No | 31 | 31 | 0 | 0 | 0 | 0 | 31 | 31 | 344.21 | 344.21 | 0 | 0 | 0 | 0 | 344.21 | 344.21 | 9.835% | 560842.0056 | 560842.0056 | 0 | 0 | 0 | 0 | 560842.0056 | 560842.0056 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15053926.3752 | 0 | 3.5 | 0 | 667.3588 | 0 | 0.95 | 0 | N/A | 0 | 0 | 2.6667 |  | 0 | N | N/A | 0 | N/A | N/A | 27.45 | -157.5167 | 27.33 | -107.97 | 0.819 | -1.59 | 0.817 | -1.255 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1303 | Fitchburg | Y | Overhead | 13.8 kV | 14.8672 | 0.6 | N/A | 0 | N/A | 0 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1309 | Fitchburg | Y | Overhead | 13.8 kV | 12.6921 | 0.6 | N/A | 0 | N/A | 0 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W51 | Fitchburg | Y | Overhead | 13.8 kV | 12.8499 | 7.8132 | 656 | 6451682.7322 | Estimated | 1.5 | No | No | 73 | 73 | 0 | 0 | 0 | 0 | 73 | 73 | 483.7 | 483.7 | 0 | 0 | 0 | 0 | 483.7 | 483.7 | 32.25% | 788121.432 | 788121.432 | 0 | 0 | 0 | 0 | 788121.432 | 788121.432 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6451682.7322 | 0 | 1.5 | 0 | 286.0109 | 0 | 0.95 | 0 | N/A | 0 | 0 | 1.3333 |  | 0 | N | N/A | 0 | N/A | N/A | 183.13 | 116.4833 | 183.13 | 116.4833 | 1.183 | 0.134 | 1.183 | 0.134 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W53 | Fitchburg | Y | Overhead | 13.8 kV | 14.6856 | 0.080643 | 1 | 32109962.1222 | Estimated | 7.4655 | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 32109962.1222 | 0 | 7.4655 | 0 | 1423.4736 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 0 | -18.95 | 0 | -18.95 | 0 | -0.33333 | 0 | -0.33333 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W54 | Fitchburg | Y | Overhead | 13.8 kV | 18.357 | 0 | N/A | 0 | N/A | 0 | No | No | [25 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W55 | Fitchburg | Y | Overhead | 13.8 kV | 8.7196 | 6.9982 | 191 | 21075496.9253 | Estimated | 4.9 | No | No | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 65.55 | 65.55 | 0 | 0 | 0 | 0 | 65.55 | 65.55 | 1.338% | 106804.548 | 106804.548 | 0 | 0 | 0 | 0 | 106804.548 | 106804.548 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 21075496.9253 | 0 | 4.9 | 0 | 934.3024 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0 |  | 0 | N | N/A | 0 | N/A | N/A | 16.14 | -6.3367 | 16.14 | -3.8067 | 0.173 | -0.074 | 0.173 | -0.058333 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W56 | Fitchburg | Y | Overhead | 13.8 kV | 9.1785 | 4.2771 | 149 | 19499005.8138 | Estimated | 4.5335 | No | No | 14 | 14 | 0 | 0 | 0 | 0 | 14 | 14 | 1046.33 | 1046.33 | 0 | 0 | 0 | 0 | 1046.33 | 1046.33 | 23.08% | 1704848.2488 | 1704848.2488 | 0 | 0 | 0 | 0 | 1704848.2488 | 1704848.2488 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 19499005.8138 | 0 | 4.5335 | 0 | 864.4146 | 0 | 0.95 | 0 | N/A | 0 | 0 | 0.66667 |  | 0 | N | N/A | 0 | N/A | N/A | 0 | -36.2367 | 0 | -35.6133 | 0 | -0.755 | 0 | -0.75067 | N/A | N/A | N/A | N/A | N/A | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | [38 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | 0 | N | N/A | 0 | N/A | N/A | [8 empty] | N/A | N/A | N/A | N/A | N/A | 0
TOTALS | [17 empty] | 1643 | 1642 | 4 | 4 | 0 | 0 | 1647 | 1646 | 29555.125 | 29206.765 | 1862.4 | 1862.4 | 0 | 0 | 31417.525 | 31069.165 |  | 48155938.47 | 47588334.6204 | 16314624 | 16314624 | 0 | 0 | 64470562.47 | 63902958.6204 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 451348669 | 0 | 112.3226 | 0 | 21417 | 0 |  |  | 0 | 0 | 0 | 34.3333 |  |  |  |  | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
NOTES
Data in entry cells of template is for reference only and should be overwritten with actual Company provided data. Please add rows for each additional substation/feeder as necessary.
Feeder/Substation Identification & Location
(1) For each feeder reported, identify all cities and towns (separated by commas) where customers served by the feeder are located.
(2) Enter "Y" for a feeder that is included in an Annual Report for the first time or "N" for a feeder that was included in a previous Annual Report.
(3) For each substation reported, a company should include a row that allows the company to identify DMS Power Flow capabiltiy .
Feeder Characteristics
(4) Enter (i) "Metered" for feeders where Energy Delivered value is based on metered data, or (ii) "Estimated" for feeders where Energy Delivered value is based on estimated data.
Feeder Capability
(5) Enter (i) "Full" for feeders that are fully automated; (ii) "Partial" for feeders that are partially automated; or (iii) "No" for feeders that are not automated.
(6) Enter (i) "Full" for feeders that are VVO-enabled with remote control capability; (ii) "Partial" for feeders that are VVO-enabled without remote control capability; or (iii) "No" for feeders that are not VVO-enabled.
DER Interconnections
(7) Insert additional columns as needed to provide the specified information for all DER types interconnected to the distribution system. DER types include various power generation fuels, storage, Level 2 EV charging stations, DC fast charging stations, and any other DER types that are interconnected to the distribution system.
Performance Metrics - Statewide
(8) For each feeder, the baseline for this metric should be the annual average of voltage complaints for the three-year period, 2015-2017, as set forth in Table 9 (Pre-Investment Baselines).
(9) Enter "Y" for substations where all feeders are modeled daily with no unwarranted voltage or capacity violations over a consecutive 30-day period.
(10) Enter "Y" for feeders where the devices deployed on the feeder can be automatically controlled by DMS commands.
(11) For each feeder, the baseline for SAIDI/SAIFI should be the annual average of SAIDI/SAIFI for the three-year period, 2015-2017, as set forth in Table 9 (Pre-Investment Baselines).
Performance Metrics - Company Specific
(12) Eversource only: Enter (i) "Static" for feeders where the company has static analysis ability, (ii) "Semi-auto 1" for feeders where the company has semi-automatic 1 analysis ability, (iii) "Semi-auto 2" for feeders where the company has semi-automatic 2 analysis ability, or (iv) "Full" for feeders where the company has full automated analysis ability.
(13) National Grid only: For each feeder, enter the customer minutes of interruption during the plan year that result from mainline interruptions.
(14) Unitil only: For each feeder, calculate the total number of customer minute saved during the plan year as the sum of the customer minutes saved per outage on the feeder, as provided in Table 8 (Unitil – Customer Minutes Saved).
Unitil Note 1 - | VVO has not been enabled for any circuits, therefore there are no voltage complaints related to VVO
Note on AJ14: Bonazoli, John: Assume 1640 Hrs/yr/kW (Net Metering filing) per PV Watts, defaults for Fitchburg, MA
Note on AL14: Bonazoli, John: Assume 1640 Hrs/yr/kW (Net Metering filing) per PV Watts, defaults for Fitchburg, MA
Note on AN14: Bonazoli, John: Assume 1640 Hrs/yr/kW (Net Metering filing) per PV Watts, defaults for Fitchburg, MA
Note on BD14: Bonazoli, John: Calculated dist. Losses at system peak (92,178 kW) = 2460 kW . Total annual system losees (kWh) = 21,4170
Note on BF14: Bonazoli, John: Based on assumptions used in power lfow modeling
Note on P24: Bonazoli, John:

## 4. System Status
TABLE 4 | System Status |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
This table presents the required format for the system-level reporting of grid modernization capabilities and performance metrics:
(1) Automation Capability
(2) VVO Capability
(3) DMS Power Flow and Control Capabilities (Y/N)
(4) Control Function Capability
(5) Load Flow Modeling Capability
(6) (Eversource only) Advanced Load Flow Capability
|  | Grid Modernization Capabilities | [5 empty] | Performance Metrics - Statewide |  |  | Performance Metrics - Company Specific
|  | Automation Capability |  |  | VVO Capability |  |  | Load Flow Modeling Capability | Control Functions | # Customers Benefitting from GMP Investments | Eversource - Advanced Load Flow Capability |  |  |  | National Grid - Main Line Interruptions | Unitil - Customer Minutes Saved
Company Name | System Wide Status | Fully Automated | Partially Automated | Not Automated | VVO-Enabled w/Remote Control Capability | VVO-Enabled w/o Remote Control Capability | Not VVO-Enabled | DMS Power Flow Modeled and Control Capabilities | Control Function | Automated Zone Size Reduced | Static | Semi-Automatic 1 | Semi-Automatic 2 | Fully Automated | Change in Customer Minutes of Interruption | Customer Minutes Saved
Unitil - FG&E | # of Feeders (1) | 0 | 0 | 45 | 0 | 0 | 45 | N/A | N/A |  | N/A | N/A | N/A | N/A
Unitil - FG&E | % Total Feeders (1) | 0% | 0% | 100% | 0% | 0% | 100% | N/A | N/A |  | N/A | N/A | N/A | N/A
Unitil - FG&E | # of Customers (2) | 0 | 0 | 29869 | 0 | 0 | 29869 | N/A | N/A | 0 | N/A | N/A | N/A | N/A
Unitil - FG&E | % of Total Customers (2) | 0% | 0% | 100% | 0% | 0% | 100% | N/A | N/A | 0% | N/A | N/A | N/A | N/A
Unitil - FG&E | Feeder Load (MWh) (3) | 0 | 0 | 451348.669 | 0 | 0 | 451348.669 | N/A | N/A |  | N/A | N/A | N/A | N/A
Unitil - FG&E | % of Total Load (3) | 0% | 0% | 100% | 0% | 0% | 100% | N/A | N/A |  | N/A | N/A | N/A | N/A
Unitil - FG&E | Peak Demand (MW) (4) | 0 | 0 | 93.323 | 0 | 0 | 93.323 | N/A | N/A |  | N/A | N/A | N/A | N/A
Unitil - FG&E | % Total Peak Demand (4) | 0% | 0% | 100% | 0% | 0% | 100% | N/A | N/A |  | N/A | N/A | N/A | N/A
[14 empty] | # Minutes | N/A | 0
Notes
(1) Enter number of feeders that have attained the specified grid modernization capability and percentage of total feeders that the number represents.
(2) Enter number of customers served by feeders that have attained the specified grid modernization capability and percentage of total customers that the number represents.
(3) Enter annual energy delivered (in MWh) by feeders that have attained the specified grid modernization capability and percentage of energy delivered systemwide the MWh represent.
(4) Enter (coincident) peak demand (in MW) of feeders that have attained the specified grid modernization capability and percentage of system peak demand the MW represent.

## 5.a. Spending - 2018 Report
TABLE 5a | System Spending - 2018 Report |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
This table presents the required format for the reporting of the system-level deployment and spending information in the 2018 Annual Report.
|  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 3-Yr Term
Company Name | Investment Category | Preauthorized Device Type | Actual # of Devices Deployed, 2018 | Actual Total Spending, 2018 ($) | Actual Spending on Investments Placed In-Service, 2018 ($) | Projected # of Devices to be Deployed, 2019 | Projected Total Spending, 2019 ($) | Projected Spending on Investments Placed In-Service, 2019 ($) | Projected # of Devices to be Deployed, 2020 | Projected Total Spending, 2020 ($) | Projected Spending on Investments Placed In-Service, 2020 ($) | Projected # of Devices to be Deployed, 3-Yr Term | Projected Total Spending - 3-Yr Term ($) | Projected Spending on Investments Placed In-Service, 3-Yr Term ($)
Unitil - FG&E | Monitoring & Control (SCADA) | Microprocessor Relay | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15000 | 15000 | 2 | 15000 | 15000
Unitil - FG&E | Monitoring & Control (SCADA) | 4kV Circuit Breaker SCADA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Monitoring & Control (SCADA) | Recloser SCADA | 0 | 0 | 0 | 5 | 682500 | 682500 | 4 | 120000 | 120000 | 9 | 802500 | 802500
Unitil - FG&E | Monitoring & Control (SCADA) | Padmount Switch SCADA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Monitoring & Control (SCADA) | Network Protector SCADA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Monitoring & Control (SCADA) | OMS/AMI Integration | 0 | 0 | 0 |  | 70000 | 0 | 1 | 35000 | 105000 | 1 | 105000 | 105000
Unitil - FG&E | Distribution Automation | OH DA w/o Ties | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Distribution Automation | OH DA w/Ties | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Distribution Automation | 4kV Oil Switch Replacement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Distribution Automation | 4kV VFI Retrofit for DA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Volt-Var Optimization | VVO - Regulators | 0 | 0 | 0 | 12 | 739000 | 739000 | 24 | 739000 | 739000 | 36 | 1478000 | 1478000
Unitil - FG&E | Volt-Var Optimization | VVO - Capacitor Banks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | Volt-Var Optimization | VVO - LTC Controls | 0 | 0 | 0 | 1 | 37500 | 37500 | 0 | 0 | 0 | 1 | 37500 | 37500
Unitil - FG&E | Volt-Var Optimization | VVO - Line Sensors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unitil - FG&E | Volt-Var Optimization | VVO - IT Work | 0 | 0 | 0 | Note 1 | Note 1 | Note 1 | Note 1 | Note 1 | Note 1 | Note 1 | Note 1 | Note 1
Unitil - FG&E | Advanced Distribution Management System (ADMS) | Advanced Load Flow | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Advanced Distribution Management System (ADMS) | GIS Survey (Expense) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | Advanced Distribution Management System (ADMS) | Dist. Management System | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 700000 | 0 | 1 | 700000 | 0
Unitil - FG&E | Communications | Numbers of Nodes | Note 2 | Note 2 | Note 2 | Note 3 | 280000 | 280000 | Note 3 | 280000 | 280000 | N/A | N/A | N/A
Unitil - FG&E | Communications | Miles of Fiber | Note 2 | Note 2 | Note 2 | Note 3 | Note 3 | Note 3 | Note 3 | Note 3 | Note 3 | Note 3 | Note 3 | Note 3
Unitil - FG&E | Workforce Management | Mobile Damage Assessment | 0 | 0 | 0 | 1 | 300000 | 300000 | 1 | 100000 | 100000 | 2 | 400000 | 400000
|  | TOTAL | 0 | 0 | 0 | 19 | 2109000 | 2039000 | 33 | 1989000 | 1359000 | 52 | 3538000 | 2838000
Note 1 - IT work was not estimated separately from the field equipment. Assumed to be part of ADMS.
Note 2 - Communications study was required before system could be installed.
Note 3 - Specific quantities not known until communications study is completed

## 5.b. Spending - 2019 Report
TABLE 5b | System Spending - 2019 Report |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
This table presents the required format for the reporting of the system-level deployment and spending information in the 2019 Annual Report.
|  |  | 2019 | [8 empty] | 2020 | [8 empty] | 3-Yr Term
|  |  | Reported Projection |  |  | Actual |  |  | % Difference |  |  | Reported Projection |  |  | Revised Projection |  |  | % Difference |  |  | Reported Projection |  |  | Revised Projection |  |  | % Difference
Company Name | Investment Category | Preauthorized Device Type | Reported Projected Deployment (# of Devices) | Reported Projected Spending, Total ($) | Reported Projected Spending, In-Service ($) | Actual Deployment (# of Devices) | Actual Spending, Total ($) | Actual Spending, In-Service ($) | % Difference, Actual vs. Reported Projected Deployment | % Difference, Actual vs. Reported Projected Spending, Total | % Difference, Actual vs. Reported Spending, In-Service | Reported Projected Deployment (# of Devices) | Reported Projected Spending, Total ($) | Reported Projected Spending, In-Service ($) | Revised Projected Deployment (# of Devices) | Revised Projected Spending, Total ($) | Revised Projected Spending, In-Service ($) | % Difference, Revised vs. Reported Projected Deployment | % Difference, Revised vs. Reported Projected Spending, Total | % Difference, Revised vs. Reported Projected Spending, In-Service | Reported Projected Deployment (# of Devices) | Reported Projected Spending, Total ($) | Reported Projected Spending, In-Service ($) | Revised Projected Deployment (# of Devices) | Revised Projected Spending, Total ($) | Revised Projected Spending, In-Service ($) | % Difference, Revised vs. Reported Projected Deployment | % Difference, Revised vs. Reported Projected Spending, Total | % Difference, Revised vs. Reported Projected Spending, In-Service
Unitil - FG&E | Monitoring & Control (SCADA) | Microprocessor Relay | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Monitoring & Control (SCADA) | 4kV Circuit Breaker SCADA | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Monitoring & Control (SCADA) | Recloser SCADA | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Monitoring & Control (SCADA) | Padmount Switch SCADA | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Monitoring & Control (SCADA) | Network Protector SCADA | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Monitoring & Control (SCADA) | OMS/AMI Integration | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Distribution Automation | OH DA w/o Ties | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Distribution Automation | OH DA w/Ties | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Distribution Automation | 4kV Oil Switch Replacement | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Distribution Automation | 4kV VFI Retrofit for DA | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Volt-Var Optimization | VVO - Regulators | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Volt-Var Optimization | VVO - Capacitor Banks | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Volt-Var Optimization | VVO - LTC Controls | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Volt-Var Optimization | VVO - Line Sensors | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Volt-Var Optimization | VVO - IT Work | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Advanced Distribution Management System (ADMS) | Advanced Load Flow | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Advanced Distribution Management System (ADMS) | GIS Survey (Expense) | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Advanced Distribution Management System (ADMS) | Dist. Management System | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Communications | Numbers of Nodes | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Communications | Miles of Fiber | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
Unitil - FG&E | Workforce Management | Mobile Damage Assessment | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0%
|  | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## 6. Substation Information
TABLE 6 | Substation Information |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
This table presents the required format for the reporting of general substation level information.
Company Name | Substation Name | Substation Location (Division) | Substation Location (District) | Substation Location (City/Town) | # of Feeders Served Off of Substation | # of Customers Served by Substation | Annual Energy Delivered by Substation (in MWh) | Substation Peak Demand (in MW)
Unitil - FG&E | Beech Street | N/A | N/A | Fitchburg | 4 | 3971 | 43075735.0421 | 9000
Unitil - FG&E | Canton Street | N/A | N/A | Fitchburg | 3 | 2826 | 25798822.1493 | 5982
Unitil - FG&E | Townsend | N/A | N/A | Townsend | 4 | 2058 | 45440565.3939 | 10270
Unitil - FG&E | Nockege | N/A | N/A | Fitchburg | 2 | 1125 | 8625830.5437 | 1944
Unitil - FG&E | Wallace Road | N/A | N/A | Fitchburg | 1 | 1 | 205582.5239 | 2983
Unitil - FG&E | Sawyer Passway | N/A | N/A | Fitchburg | 9 | 2567 | 38858971.5803 | 9200
Unitil - FG&E | River Street | N/A | N/A | Fitchburg | 3 | 1895 | 16747737.1928 | 3600
Unitil - FG&E | Lunenburg | N/A | N/A | Lunenburg | 2 | 2965 | 37284566.4771 | 8469
Unitil - FG&E | Pleasant Street | N/A | N/A | Lunenburg | 3 | 3740 | 38518246.9855 | 7951
Unitil - FG&E | Rindge Road | N/A | N/A | Fitchburg | 1 | 761 | 12624663.8696 | 2935
Unitil - FG&E | West Townsend | N/A | N/A | Townsend | 2 | 3264 | 34063289.5939 | 7043
Unitil - FG&E | Summer Street | N/A | N/A | Fitchburg | 6 | 3699 | 70968510.0544 | 13400
Unitil - FG&E | Princeton Road | N/A | N/A | Fitchburg | 5 | 997 | 79136147.5935 | 17625
Unitil - FG&E | TOTALS |  |  |  | 45 | 29869 | 451348669 | 100402
Note: Data in entry cells of template is for reference only and should be overwritten with actual Company provided data. Please add rows for each additional substation as necessary.

## 7. DMS Power Flow
Table 7 | DMS Power Flow and Control Capabilities |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
Feeder/Substation Identification & Location |  |  | DMS-Power Flow and Control Capabilities
Company Name | Substation Name | Feeder ID (1) | Full or Partial (2) | # of Warranted Voltage Violations during Consecutive 30-Day Testing Period | # of Unwarranted Voltage Violations during Consecutive 30-Day Testing Period | # of Warranted Capacity Violations during Consecutive 30-Day Testing Period | # of Unwarranted Capacity Violations during Consecutive 30-Day Testing Period | Explanation of Warranted Violations
Unitil - FG&E | Beech Street | 1W1 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Beech Street | 1W2 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Beech Street | 1W4 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Beech Street | 1W6 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Beech Street
Unitil - FG&E | Canton Street | 11H10 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Canton Street | 11H11 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Canton Street | 11W11 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Canton Street
Unitil - FG&E | Townsend | 15W14 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Townsend | 15W15 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Townsend | 15W16 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Townsend | 15W17 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Townsend
Unitil - FG&E | Nockege | 20H22 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Nockege | 20H24 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Nockege
Unitil - FG&E | Wallace Road | 1341 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Wallace Road
Unitil - FG&E | Sawyer Passway | 22W1 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | 22W2 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | 22W3 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | 22W8 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | 22W10 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | 22W11 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | 22W12 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | 22W17 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway | Network | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Sawyer Passway
Unitil - FG&E | River Street | 25W27 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | River Street | 25W28 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | River Street | 25W29 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | River Street
Unitil - FG&E | Lunenburg | 30W30 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Lunenburg | 30W31 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Lunenburg
Unitil - FG&E | Pleasant Street | 31W34 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Pleasant Street | 31W37 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Pleasant Street | 31W38 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Pleasant Street
Unitil - FG&E | Rindge Road | 35W36 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Rindge Road
Unitil - FG&E | West Townsend | 39W18 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | West Townsend | 39W19 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | West Townsend
Unitil - FG&E | Summer Street | 40W38 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Summer Street | 40W39 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Summer Street | 40W40 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Summer Street | 40W42 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Summer Street | 1303 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Summer Street | 1309 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Summer Street
Unitil - FG&E | Princeton Road | 50W51 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Princeton Road | 50W53 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Princeton Road | 50W54 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Princeton Road | 50W55 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Princeton Road | 50W56 | None | N/A | N/A | N/A | N/A | DMS power flow functionality not yet deployed
Unitil - FG&E | Princeton Road

## 8. Unitil CMI
Table 8 | Unitil Customer Minutes Saved |  | Company Name | Unitil - FG&E
|  |  | Plan Year | 2018
Feeder/Substation Identification & Location |  | Outage and Customer Impact Information
Substation Name | Feeder ID (1) | Outage # (2) | Time of First Notification from AMI to OMS (Minutes) | Time of First Notification from IVR to OMS (Minutes) | # of Minutes Saved During Outage (3) | # of Customers Affected by Outage | Customer Minutes Saved (4)
Beech Street | 1W1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Beech Street | 1W2 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Beech Street | 1W4 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Beech Street | 1W6 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Beech Street | [5 empty] | Feeder Total | #VALUE!
Canton Street | 11H10 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Canton Street | 11H11 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Canton Street | 11W11 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Canton Street | [5 empty] | Feeder Total | #VALUE!
Townsend | 15W14 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Townsend | 15W15 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Townsend | 15W16 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Townsend | 15W17 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Townsend | [5 empty] | Feeder Total | #VALUE!
Nockege | 20H22 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Nockege | 20H24 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Nockege | [5 empty] | Feeder Total | #VALUE!
Wallace Road | 1341 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Wallace Road | [5 empty] | Feeder Total | #VALUE!
Sawyer Passway | 22W1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | 22W2 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | 22W3 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | 22W8 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | 22W10 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | 22W11 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | 22W12 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | 22W17 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | Network | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Sawyer Passway | [5 empty] | Feeder Total | #VALUE!
River Street | 25W27 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
River Street | 25W28 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
River Street | 25W29 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
River Street | [5 empty] | Feeder Total | #VALUE!
Lunenburg | 30W30 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Lunenburg | 30W31 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Lunenburg | [5 empty] | Feeder Total | #VALUE!
Pleasant Street | 31W34 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Pleasant Street | 31W37 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Pleasant Street | 31W38 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Pleasant Street | [5 empty] | Feeder Total | #VALUE!
Rindge Road | 35W36 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Rindge Road | [5 empty] | Feeder Total | #VALUE!
West Townsend | 39W18 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
West Townsend | 39W19 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
West Townsend | [5 empty] | Feeder Total | #VALUE!
Summer Street | 40W38 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Summer Street | 40W39 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Summer Street | 40W40 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Summer Street | 40W42 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Summer Street | 1303 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Summer Street | 1309 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Summer Street | [5 empty] | Feeder Total | #VALUE!
Princeton Road | 50W51 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Princeton Road | 50W53 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Princeton Road | 50W54 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Princeton Road | 50W55 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Princeton Road | 50W56 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | Unitil Note 1 | #VALUE!
Princeton Road | [5 empty] | Feeder Total | #VALUE!
Notes
Data in entry cells of template is for reference only and should be overwritten with actual Company provided data. Please add rows for each additional substation/feeder as necessary.
(1) Provide the specified information for each feeder included in Table 3 (Feeder Status).
(2) List every outage that occurred on the applicable feeder during the plan year.
Unitil Note 1 - | There were no grid mod projects completed in 2018 that would have saved customer minutes.

## 9. Pre-Investment Baselines
Table 9 | Grid Modernization Performance Metrics Pre-Investment Baselines for All Feeders |  |  |  |  | Company Name | Unitil - FG&E
[6 empty] | Plan Term | 2018
Feeder/Substation Identification & Location | [6 empty] | Feeder Characteristics in 2017 |  |  |  |  | DER Interconnections in 2017 | [24 empty] | State-Wide Performance Metrics Pre-investment Baselines | [15 empty] | Company-Specific Performance Metrics Pre-Investment Baselines
[12 empty] | # of DER Facilities | [7 empty] | Nominal DER Capacity (in kW) | [8 empty] | Estimated Annual DER Energy Output (in kWh) | [7 empty] | VVO-Related | [10 empty] | Reliability Related |  |  |  |  | Eversource |  |  |  |  | National Grid
[12 empty] | Solar |  | Gas |  | DER Type 3 [N/A] |  | Total (All DER Types) |  | Solar |  | Gas |  | DER Type 3 [N/A] |  | Total (All DER Types) |  | % DER Capacity to Peak Demand | Solar |  | Gas |  | DER Type 3 [N/A] |  | Total (All DER Types) |  | VVO Energy Savings (Performance Metric Compliance Filing, § 2.2) |  |  |  | VVO Peak Load Impact (Performance Metric Compliance Filing, § 2.3) |  |  | VVO-Related Voltage Complaints (Performance Metric Compliance Filing, § 2.12) |  |  |  | Outage Duration and Frequency (Performance Metrics Compliance Filing, § 2.10 & § 2.11) |  |  |  |  | Advanced Load Flow Milestone Completion (Performance Metrics Compliance Filing, §A.1.0) |  |  |  | Averag Outage Zone Size (Performance Metrics Compliance Filing, §A.2.0) | Main Line Customer Minutes of Interruption (Performance Metrics Compliance Filing, §C.1.0)
[37 empty] | Annual Energy Delivered (kWh) |  |  |  | Annual Peak Load (MVA) |  |  | # of Voltage Complaints | [8 empty] | Milestone Completion in 2017
Company Name | Division Name | District Name | Substation Name | Substation Location (City/Town) | Feeder ID | Feeder Location (Cities/Towns) (1) | Feeder Type (Overhead/ Underground) | System Voltage (in kV) | Feeder Capacity Rating (in MVA) | Feeder Length (in miles) | Current Customers Count | Total # of Facilities Interconnected on Feeder | # of Customer-Owned Facilities Interconnected on Feeder | Total # of Facilities Interconnected on Feeder | # of Customer-Owned Facilities Interconnected on Feeder | Total # of Facilities Interconnected on Feeder1 57 43 | # of Customer-Owned Facilities Interconnected on Feeder | Total # of DER Facilities Interconnected on Feeder | # of Customer-Owned DER Facilities Interconnected on Feeder | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (in kW) | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (in kW) | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (in kW) | Nominal Capacity of All Facilities Interconnected on Feeder (in kW) | Nominal Capacity of Customer-Owned Facilities Interconnected on Feeder (kW) | Total Nominal Capacity (all DER types)/Feeder Peak Demand | Estimated Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of All Facilities Interconnected on Feeder (in kWh) | Estimated Annual Energy Output of Customer-Owned Facilities Interconnected on Feeder (in kWh) | 2015 | 2016 | 2017 | Metered or Estimated | 2015 | 2016 | 2017 | 2015 | 2016 | 2017 | 2015-2017 Average | Circuit Level SAIDI, 2015-2017 average, w/Excludable Major Events | Circuit Level SAIDI, 2015-2017 average, w/o Excludable Major Events | Circuit Level SAIFI, 2015-2017 average, w/Excludable Major Events | Circuit Level SAIFI, 2015-2017 average, w/o Excludable Major Events | Summary of Main Causes of Outages | Static Automation (Y/N) | Semi-Automatic 1 (Y/N) | Semi-Automatic 2 (Y/N) | Fully Automated (Y/N) | Baseline: 2017 Average Outage Zone Size, in # customers | 2015 | 2016 | 2017 | Baseline: Average 2015 - 2017
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W1 | Fitchburg | Overhead | 13.8 kV | 8.9156 | 5.8371 | 374 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 400 | 400 | 0 | 0 | 0 | 0 | 400 | 400 | 10.46% | 651744 | 651744 | 0 | 0 | 0 | 0 | 689871.024 | 689871.024 | 12885167.5695 | 5452573.9892 | 5581681.0429 | Estimated | 6.5174 | 4.032 | 3.824 | 0 | 0 | 1 | 0.33333 | 157.1833 | 45.0567 | 1.7413 | 0.30933 | Tree/Limb Contact - Growth into Line Vehicle Accident | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W2 | Fitchburg | Overhead | 13.8 kV | 8.9156 | 9.3707 | 2001 | 47 | 47 | 1 | 1 | 0 | 0 | 48 | 48 | 451.835 | 451.835 | 1.2 | 0 | 0 | 0 | 453.035 | 451.835 | 15.67% | 736201.8756 | 736201.8756 | 10512 | 0 | 0 | 0 | 802133.928 | 802133.928 | 15850801.3752 | 13107233.3707 | 13242183.4094 | Estimated | 3.7049 | 2.988 | 2.892 | 2 | 0 | 1 | 1 | 167.5133 | 42.64 | 2.419 | 1.086 | Patrolled, Nothing Found Squirrel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W4 | Fitchburg | Overhead | 13.8 kV | 9.5609 | 8.9631 | 1628 | 30 | 30 | 0 | 0 | 0 | 0 | 30 | 30 | 445.08 | 445.08 | 0 | 0 | 0 | 0 | 445.08 | 445.08 | 20.77% | 725195.5488 | 725195.5488 | 0 | 0 | 0 | 0 | 1132698.4848 | 1132698.4848 | 10294498.9576 | 10238381.0868 | 9812586.1156 | Estimated | 2.4062 | 2.334 | 2.143 | 2 | 1 | 1 | 1.3333 | 162.9167 | 62.0233 | 2.4853 | 1.3633 | Patrolled, Nothing Found Squirrel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg | 1W6 | Fitchburg | Overhead | 13.8 kV | 8.9156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Circuit did not supply customers during this timeframe | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Beech Street | Fitchburg
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H10 | Fitchburg | Overhead | 4.16 kV | 2.0175 | 3.866 | 734 | 22 | 22 | 0 | 0 | 0 | 0 | 22 | 22 | 128.785 | 128.785 | 0 | 0 | 0 | 0 | 128.785 | 128.785 | 14.26% | 209837.1276 | 209837.1276 | 0 | 0 | 0 | 0 | 209837.1276 | 209837.1276 | 4346632.0966 | 4329598.1717 | 4134748.1392 | Estimated | 1.016 | 0.987 | 0.903 | 0 | 0 | 0 | 0 | 133.3367 | 51.5933 | 2.29 | 1.1437 | Vehicle Accident Patrolled, Nothing Found | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11H11 | Fitchburg | Overhead | 4.16 kV | 2.0175 | 2.6698 | 367 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 25.23 | 25.23 | 0 | 0 | 0 | 0 | 25.23 | 25.23 | 2.707% | 41108.7528 | 41108.7528 | 0 | 0 | 0 | 0 | 41108.7528 | 41108.7528 | 4028084.5907 | 4075173.963 | 4267536.2855 | Estimated | 0.9415 | 0.929 | 0.932 | 0 | 0 | 0 | 0 | 132.6 | 61.88 | 2.0993 | 1.1027 | Equipment Failure Company Bird | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg | 11W11 | Fitchburg | Overhead | 13.8 kV | 12.6921 | 19.6011 | 1705 | 78 | 78 | 0 | 0 | 0 | 0 | 78 | 78 | 576.85 | 576.85 | 0 | 0 | 0 | 0 | 576.85 | 576.85 | 14.36% | 939896.316 | 939896.316 | 0 | 0 | 0 | 0 | 939896.316 | 939896.316 | 21611630.262 | 18941443.673 | 18388868.8009 | Estimated | 5.0514 | 4.318 | 4.016 | 0 | 2 | 2 | 1.3333 | 90.7367 | 66.8367 | 1.5257 | 0.82833 | Vehicle Accident Tree/Limb - Broken Limb | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Canton Street | Fitchburg
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W14 | Townsend | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Circuit did not supply customers during this timeframe | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W15 | Townsend | Overhead | 13.8 kV | 9.5609 | 0.075962 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16498468.5281 | 16879730.2579 | 17802769.3969 | Estimated | 3.8562 | 3.848 | 3.888 | 0 | 0 | 0 | 0 | 90.91 | 0 | 1 | 0 | n/a | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W16 | Townsend, Lunenburg | Overhead | 13.8 kV | 7.6487 | 41.116 | 1496 | 127 | 127 | 0 | 0 | 0 | 0 | 127 | 127 | 960.39 | 960.39 | 0 | 0 | 0 | 0 | 960.39 | 960.39 | 19.44% | 1564821.0504 | 1564821.0504 | 0 | 0 | 0 | 0 | 1564821.0504 | 1564821.0504 | 20043593.997 | 21599737.9911 | 22619773.8736 | Estimated | 4.6849 | 4.924 | 4.94 | 2 | 1 | 0 | 1 | 246.8333 | 87.1367 | 2.7277 | 1.3173 | Tree/Limb Contact - Broken Limb Squirrel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Townsend | Townsend | 15W17 | Townsend | Overhead | 13.8 kV | 9.5609 | 11.4409 | 552 | 48 | 48 | 0 | 0 | 0 | 0 | 48 | 48 | 314.025 | 314.025 | 0 | 0 | 0 | 0 | 314.025 | 314.025 | 20.63% | 511659.774 | 511659.774 | 0 | 0 | 0 | 0 | 511659.774 | 511659.774 | 6578934.7643 | 6185140.2452 | 6969088.2258 | Estimated | 1.5377 | 1.41 | 1.522 | 0 | 0 | 1 | 0.33333 | 233.1867 | 52.2867 | 2.0877 | 0.695 | Squirrel Tree/Limb Contract - Broken Limb | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Townsend | Townsend
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H22 | Fitchburg | Overhead | 4.16 kV | 2.1616 | 15.6295 | 900 | 56 | 56 | 1 | 1 | 0 | 0 | 57 | 57 | 358.95 | 358.95 | 8 | 8 | 0 | 0 | 366.95 | 366.95 | 26.31% | 584858.772 | 584858.772 | 66576 | 66576 | 0 | 0 | 651434.772 | 651434.772 | 7768448.8535 | 7018598.8598 | 6378409.9202 | Estimated | 1.8157 | 1.6 | 1.393 | 0 | 0 | 0 | 0 | 164.98 | 103.4033 | 3.1767 | 2.7697 | Tree/Limb Contact - Broken Limb Action by Others | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg | 20H24 | Fitchburg | Overhead | 4.16 kV | 2.1616 | 2.0171 | 240 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 372.42 | 372.42 | 0 | 0 | 0 | 0 | 372.42 | 372.42 | 100.7% | 606806.2512 | 606806.2512 | 0 | 0 | 0 | 0 | 606806.2512 | 606806.2512 | 5651649.2982 | 1886248.4436 | 1694193.5897 | Estimated | 1.321 | 0.43 | 0.37 | 0 | 0 | 0 | 0 | 145.58 | 84.92 | 2.9467 | 2.6077 | Equipment Failure Company Action by Others | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Nockege | Fitchburg
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg | 1341 | Fitchburg | Overhead | 13.8 kV | 5.9039 | 2.7 | N/A | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079352.4385 | 1013310.2104 | 0 | Estimated | 3.5057 | 2.789 | 2.605 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Outage Statistics Part of 1W1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Wallace Road | Fitchburg
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W1 | Fitchburg | Underground | 13.8 kV | 9.3219 | 11.7727 | 2054 | 25 | 25 | 2 | 2 | 0 | 0 | 27 | 27 | 311.22 | 311.22 | 61.2 | 61.2 | 0 | 0 | 372.42 | 372.42 | 8.13% | 507089.4192 | 536112 | 536112 | 536112 | 0 | 0 | 1043201.4192 | 1072224 | 20588997.9153 | 21003157.088 | 20975948.2014 | Estimated | 4.8123 | 4.788 | 4.581 | 2 | 2 | 1 | 1.6667 | 129.8567 | 55.7167 | 1.6043 | 0.92133 | Equipment Failure Company Tree/Limb Contact - Broken Trunk | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W2 | Fitchburg | Underground | 13.8 kV | 3.5853 | 1.1876 | Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 0.77284 | 0.749 | 0.629 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Reference Newtork Below | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W3 | Fitchburg | Underground | 13.8 kV | 3.7049 | 0.80366 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3170160.275 | 2969744.6426 | 3173178.8045 | Estimated | 0.74097 | 0.677 | 0.693 | 0 | 0 | 0 | 0 | 17.8 | 17.8 | 0.33333 | 0.33333 | Equipment Faillure Company | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W8 | Fitchburg | Underground | 13.8 kV | 8.5331 | 1.4224 | Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 0.83658 | 0.574 | 0.558 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Reference Newtork Below | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W10 | Fitchburg | Underground | 13.8 kV | 8.5331 | 1.7918 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 2.2787 | 1.944 | 1.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W11 | Fitchburg | Underground | 13.8 kV | 8.5331 | 1.2636 | Network | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 1.6174 | 1 | 1.195 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Reference Newtork Below | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W12 | Fitchburg | Underground | 13.8 kV | 2.295 | 0.25012 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | 1629360 | 0 | 0 | 0 | 0 | 0 | 1629360 | 0 | 0 | 0 | 0 | Estimated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Supplies Unitil PV Site | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | 22W17 | Fitchburg | Underground | 13.8 kV | 8.5331 | 1.717 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4567757.8156 | 4386624.2874 | 4853635.6895 | Estimated | 1.0676 | 1 | 1.06 | 0 | 0 | 0 | 0 | 33.4167 | 32.86 | 1.111 | 0.83333 | Equipment Failure Company Action by Others | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg | Network | Fitchburg | Underground | 208 V | 9.8 | N/A | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12748816.5899 | 10190128.2196 | 10906943.5965 | Estimated | 2.9798 | 2.323 | 2.382 | 1 | 0 | 0 | 0.33333 | 75.0457 | 17.1367 | 0.66475 | 0.32533 | Action By Others Equipment Failure Company | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Sawyer Passway | Fitchburg
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W27 | Fitchburg | Overhead | 13.8 kV | 9.5609 | 12.9608 | 1194 | 72 | 72 | 0 | 0 | 0 | 0 | 72 | 72 | 645.54 | 645.54 | 0 | 0 | 0 | 0 | 645.54 | 645.54 | 31.16% | 1051817.0544 | 1051817.0544 | 0 | 0 | 0 | 0 | 1051817.0544 | 1051817.0544 | 10021796.9985 | 10589311.0298 | 9487484.1024 | Estimated | 2.3424 | 2.414 | 2.072 | 0 | 2 | 2 | 1.3333 | 14.7833 | 13.96 | 0.32133 | 0.313 | Squirrel Patrolled, Nothing Found | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W28 | Fitchburg | Overhead | 13.8 kV | 7.1707 | 9.2967 | 637 | 21 | 21 | 0 | 0 | 0 | 0 | 21 | 21 | 125.31 | 125.31 | 0 | 0 | 0 | 0 | 125.31 | 125.31 | 9.588% | 204175.1016 | 204175.1016 | 0 | 0 | 0 | 0 | 204175.1016 | 204175.1016 | 8249234.2641 | 5904396.2908 | 5984624.3832 | Estimated | 1.9281 | 1.346 | 1.307 | 1 | 2 | 0 | 1 | 245.0867 | 19.3433 | 0.46167 | 0.24733 | Tree/Limb Contact - Broken Limb Vehicle Accident | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | River Street | Fitchburg | 25W29 | Fitchburg | Overhead | 13.8 kV | 9.1785 | 0.0026261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Circuit did not supply customers during this timeframe | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | River Street | Fitchburg
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W30 | Lunenburg | Overhead | 13.8 kV | 9.9434 | 45.8162 | 1308 | 102 | 102 | 0 | 0 | 0 | 0 | 102 | 102 | 1006.9 | 1006.9 | 0 | 0 | 0 | 0 | 1006.9 | 1006.9 | 22.81% | 1640602.584 | 2057181.0552 | 0 | 0 | 0 | 0 | 1640602.584 | 2057181.0552 | 19532277.8236 | 19187094.6331 | 20211271.6352 | Estimated | 4.5653 | 4.374 | 4.414 | 1 | 3 | 1 | 1.6667 | 284.5833 | 135.4133 | 2.863 | 1.886 | Squirrel Tree/Limb Contract - Broken Limb | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg | 30W31 | Lunenburg, Townsend, Fitchburg | Overhead | 13.8 kV | 11.0142 | 45.4194 | 1628 | 77 | 77 | 1 | 1 | 0 | 0 | 78 | 78 | 3443.755 | 3443.755 | 9.92 | 9.92 | 0 | 0 | 3453.675 | 3453.675 | 94.23% | 5611116.6468 | 5899171.2012 | 86899.2 | 86899.2 | 0 | 0 | 5698015.8468 | 5986070.4012 | 16907521.4668 | 17985159.5783 | 16781674.3414 | Estimated | 3.9518 | 4.1 | 3.665 | 2 | 2 | 2 | 2 | 193.0933 | 96.0867 | 2.1907 | 1.5693 | Squirrel Tree/Limb Contract - Broken Limb | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Lunenburg | Lunenburg
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W34 | Lunenburg, Fitchburg | Overhead | 13.8 kV | 12.6204 | 6.1512 | 1238 | 25 | 25 | 0 | 0 | 0 | 0 | 25 | 25 | 115.72 | 115.72 | 0 | 0 | 0 | 0 | 115.72 | 115.72 | 6.454% | 188549.5392 | 188549.5392 | 0 | 0 | 0 | 0 | 188549.5392 | 188549.5392 | 8078795.5396 | 8457411.6261 | 8209970.5578 | Estimated | 1.8883 | 1.928 | 1.793 | 5 | 0 | 0 | 1.6667 | 69.7833 | 3.8867 | 1.0683 | 0.068333 | Squirrel Patrolled, Nothing Found | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W37 | Lunenburg, Fitchburg | Overhead | 13.8 kV | 11.4731 | 22.6044 | 1219 | 103 | 103 | 0 | 0 | 0 | 0 | 103 | 103 | 1156.57 | 1156.57 | 0 | 0 | 0 | 0 | 1156.57 | 1156.57 | 33.6% | 1884468.8952 | 1884468.8952 | 0 | 0 | 0 | 0 | 1884468.8952 | 1884468.8952 | 15271309.712 | 17160474.2123 | 15760579.286 | Estimated | 3.5694 | 3.912 | 3.442 | 2 | 2 | 1 | 1.6667 | 237.5133 | 82.0933 | 2.9073 | 1.5147 | Squirrel Tree/Limb Contract - Broken Limb | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg | 31W38 | Lunenburg | Overhead | 13.8 kV | 12.6921 | 18.7711 | 1211 | 64 | 64 | 0 | 0 | 0 | 0 | 64 | 64 | 1464.605 | 1464.605 | 0 | 0 | 0 | 0 | 1464.605 | 1464.605 | 61.08% | 2386368.8028 | 2386368.8028 | 0 | 0 | 0 | 0 | 2386368.8028 | 2386368.8028 | 14214589.6203 | 12282548.0047 | 10980206.022 | Estimated | 3.3224 | 2.8 | 2.398 | 1 | 1 | 2 | 1.3333 | 215.18 | 40.28 | 2.0717 | 0.65667 | Tree/Limb Contract - Broken Limb Squirrel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Pleasant Street | Lunenburg
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg | 35W36 | Fitchburg, Ashby | Overhead | 13.8 kV | 7.6487 | 23.2707 | 760 | 82 | 82 | 0 | 0 | 0 | 0 | 82 | 82 | 521.575 | 521.575 | 0 | 0 | 0 | 0 | 521.575 | 521.575 | 20.02% | 849833.442 | 849833.442 | 0 | 0 | 0 | 0 | 849833.442 | 849833.442 | 12919255.3144 | 11220984.9271 | 11928038.652 | Estimated | 3.0197 | 2.558 | 2.605 | 1 | 4 | 0 | 1.6667 | 189.7233 | 41.3667 | 1.538 | 0.65767 | Tree/Limb Contact - Broken Limb Tree/Limb Contact - Growth into Line | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Rindge Road | Fitchburg
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W18 | Townsend, Lunenburg | Overhead | 13.8 kV | 12.6921 | 51.2203 | 1957 | 105 | 105 | 0 | 0 | 0 | 0 | 105 | 105 | 697.805 | 697.805 | 0 | 0 | 0 | 0 | 697.805 | 697.805 | 17.17% | 1136975.5548 | 1136975.5548 | 0 | 0 | 0 | 0 | 1136975.5548 | 1136975.5548 | 19123224.8849 | 19538024.576 | 18604077.1758 | Estimated | 4.4697 | 4.454 | 4.063 | 2 | 1 | 6 | 3 | 229.2367 | 68.9333 | 2.2407 | 0.86133 | Tree/Limb Contract - Broken Limb Squirrel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | West Townsend | Townsend | 39W19 | Townsend, Ashby | Overhead | 13.8 kV | 8.261 | 61.9023 | 1291 | 139 | 139 | 0 | 0 | 0 | 0 | 139 | 139 | 2854.635 | 2854.635 | 0 | 0 | 0 | 0 | 2854.635 | 2854.635 | 119.4% | 4651228.0836 | 4651228.0836 | 0 | 0 | 0 | 0 | 4651228.0836 | 4651228.0836 | 10464937.6821 | 11080612.95 | 10943574.8093 | Estimated | 2.446 | 2.526 | 2.39 | 4 | 4 | 2 | 3.3333 | 414.6067 | 99.37 | 2.922 | 1.3367 | Tree/Limb Contract - Broken Limb Squirrel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | West Townsend | Townsend
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W38 | Fitchburg | Overhead | 13.8 kV | 7.6726 | 0.60675 | 4 |  |  | 1 | 1 | 0 | 0 | 1 | 1 |  |  | 1800 | 1800 | 0 | 0 | 1800 | 1800 | 81.82% | 0 | 0 | 15768000 | 15768000 | 0 | 0 | 15768000 | 15768000 | 7431128.3866 | 9650573.4323 | 10073583.5065 | Estimated | 1.7369 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 115.5833 | 66.25 | 1.0833 | 0.75 | Equipment Failure Compnay | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W39 | Fitchburg | Overhead | 13.8 kV | 9.5609 | 7.9157 | 423 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 1017 | 1017 | 0 | 0 | 0 | 0 | 1017 | 1017 | 33.9% | 1657059.12 | 1657059.12 | 0 | 0 | 0 | 0 | 1657059.12 | 1657059.12 | 11385306.7942 | 13159872.8622 | 13736704.7815 | Estimated | 2.6611 | 3 | 3 | 1 | 0 | 1 | 0.66667 | 149.7433 | 99.1733 | 1.8703 | 1.533 | Equipment Failure Company Patrolled, Nothing Found | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W40 | Fitchburg, Ashby, Lunenburg | Overhead | 13.8 kV | 12.6921 | 18.537 | 1564 | 65 | 65 | 0 | 0 | 0 | 0 | 65 | 65 | 1321.085 | 1321.085 | 0 | 0 | 0 | 0 | 1321.085 | 1321.085 | 17.58% | 2152523.0556 | 2152523.0556 | 0 | 0 | 0 | 0 | 2152523.0556 | 2152523.0556 | 34496797.8315 | 35018421.6863 | 34401287.6745 | Estimated | 8.063 | 7.983 | 7.513 | 3 | 2 | 4 | 3 | 111.1567 | 59.77 | 1.266 | 0.90567 | Equipment Failure Company Loose/Failed Connection | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 40W42 | Fitchburg | Overhead | 13.8 kV | 9.5609 | 12.4351 | 1689 | 25 | 25 | 0 | 0 | 0 | 0 | 25 | 25 | 278.8 | 278.8 | 0 | 0 | 0 | 0 | 278.8 | 278.8 | 9.183% | 454265.568 | 454265.568 | 0 | 0 | 0 | 0 | 454265.568 | 454265.568 | 8154600.8528 | 14853109.8371 | 13901545.2389 | Estimated | 1.906 | 3.386 | 3.036 | 2 | 4 | 2 | 2.6667 | 184.9667 | 135.3 | 2.409 | 2.072 | Squirrel Tree/Limb Contract - Broken Limb | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1303 | Fitchburg | Overhead | 13.8 kV | 14.8672 | 0.6 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Circuit did not directly supply customers during this timeframe | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg | 1309 | Fitchburg | Overhead | 13.8 kV | 12.6921 | 0.6 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Estimated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | Circuit did not directly supply customers during this timeframe | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Summer Street | Fitchburg
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W51 | Fitchburg | Overhead | 13.8 kV | 12.8499 | 7.8132 | 653 | 67 | 67 | 0 | 0 | 0 | 0 | 67 | 67 | 391.54 | 391.54 | 0 | 0 | 0 | 0 | 391.54 | 391.54 | 28.09% | 637959.6144 | 637959.6144 | 0 | 0 | 0 | 0 | 637959.6144 | 637959.6144 | 14691818.0488 | 6711535.1597 | 6382988.8218 | Estimated | 3.434 | 1.53 | 1.394 | 2 | 1 | 1 | 1.3333 | 66.6467 | 66.6467 | 1.049 | 1.049 | Squirrel Equipment Failure Compnay | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W53 | Fitchburg | Overhead | 13.8 kV | 14.6856 | 0.080643 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33440077.7399 | 33693661.1515 | 34218131.6108 | Estimated | 7.8161 | 7.681 | 7.473 | 0 | 0 | 0 | 0 | 18.95 | 18.95 | 0.33333 | 0.33333 | Patrolled, Nothing Found | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W54 | Fitchburg | Overhead | 13.8 kV | 18.357 | 0 | 0 | [32 empty] | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | [9 empty] | 0
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W55 | Fitchburg | Overhead | 13.8 kV | 8.7196 | 6.9982 | 190 | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 37.175 | 37.175 | 0 | 0 | 0 | 0 | 37.175 | 37.175 | 0.779% | 60571.458 | 60571.458 | 0 | 0 | 0 | 0 | 60571.458 | 60571.458 | 20043593.997 | 21213715.0538 | 21850518.4058 | Estimated | 4.6849 | 4.836 | 4.772 | 0 | 0 | 0 | 0 | 22.4767 | 19.9467 | 0.247 | 0.23133 | Tree/Limb Contact - Broken Limb Vehicle Accident | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg | 50W56 | Fitchburg | Overhead | 13.8 kV | 9.1785 | 4.2771 | 145 | 12 | 12 | 0 | 0 | 0 | 0 | 12 | 12 | 836.3 | 836.3 | 0 | 0 | 0 | 0 | 836.3 | 836.3 | 18% | 1362633.768 | 1362633.768 | 0 | 0 | 0 | 0 | 1362633.768 | 1362633.768 | 20384471.4459 | 19919660.889 | 21268997.9034 | Estimated | 4.7645 | 4.541 | 4.645 | 1 | 0 | 1 | 0.66667 | 36.2367 | 35.6133 | 0.755 | 0.75067 | Squirrel Tree/Limb Contract - Uprooted Tree | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unitil - FG&E | N/A | N/A | Princeton Road | Fitchburg
TOTALS | [11 empty] | 1409 | 1408 | 6 | 6 |  |  | 1415 | 1414 | 21259.1 | 20259.1 | 1880.32 | 1879.12 |  |  | 23139.42 | 22138.22 |  | 34638727.176 | 33743022.7824 | 16468099.2 | 16457587.2 | 0 | 0 | 51607876.3884 | 50712171.9948
Note on AD8: Bonazoli, John: Assume 1640 Hrs/yr/kW (Net Metering filing) per PV Watts, defaults for Fitchburg, MA
Note on AF8: Bonazoli, John: Assume 1640 Hrs/yr/kW (Net Metering filing) per PV Watts, defaults for Fitchburg, MA
Note on AH8: Bonazoli, John: Assume 1640 Hrs/yr/kW (Net Metering filing) per PV Watts, defaults for Fitchburg, MA
Note on AJ8: Bonazoli, John: Assume 1640 Hrs/yr/kW (Net Metering filing) per PV Watts, defaults for Fitchburg, MA